## Sheet1
Team: Hello-World
Estimation Report
Velocity Per Team-Member:
- Karim: 5 Story-Points/Hour
- Youssef: 5 Story-Points/Hour
- Moataz: 5 Story-Points/Hour
- Mahmoud: 5 Story-Points/Hour
- Sohail: 4 Story-Points/Hour
- Basem: 4 Story-Points/Hour
- Kashlan: 4 Story-Points/Hour
- Gaafar: 4 Story-Points/Hour
- Hossam: 4 Story-Points/Hour
Average Team Velocity = 11 Story-Points/Hour
Sprint 1 Backlog |  |  | Sprint 1 (1 Week)
| User Stories (Features) | Initial Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
| Total Effort | 74 | 9 | 12 | 12 | 9 | 15 | 11 | 6
Sprint Burndown Chart
Note on J25: Initial numeric estimate (size) concluded during Sprint Review