## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | Testing a User I should have an avatar associated with their email | 2 | Karim | Youssef | Moataz
1.1 | Testing a User Should be able to Add Social Media Links to profiles | 2 | Karim | Youssef | Moataz
1.2 | Testing a User Should be able to create a profile as a member | 2 | Youssef | Moataz | Karim
1.3 | Testing a Member Should be able to view his profile | 2 | Youssef | Moataz | Karim
1.4 | Testing a Member Should be able to edit his profile | 3 | Youssef | Moataz | Karim
1.5 | Testing a Member Should be able to delete his profile | 3 | Youssef | Moataz | Karim
1.6 | Testing a Member's Profile Should be visible to other users | 2 | Youssef | Moataz | Karim
1.7 | Testing a Member Should be able to add certificates to his profile | 3 | Youssef | Moataz | Karim
1.8 | Testing a Member Should be able to add completed tasks to his profile | 5 | Youssef | Moataz | Karim
1.9 | Testing a Member Should be able to add Past Events to his Profile | 3 | Youssef | Moataz | Karim
2 | Testing a Member Should be able to remove a certificate from his profile | 2 | Youssef | Moataz | Karim
2.1 | Testing a Member Should be able to remove Past Events from his Profile | 2 | Youssef | Moataz | Karim
2.2 | Testing a User Should be able to create a Profile as a Partner | 2 | Moataz | Youssef | Karim
2.3 | Testing a Partner Should be able to View their Profile | 2 | Moataz | Youssef | Karim
2.4 | Testing a Partner Should be able to edit their Profile | 3 | Moataz | Youssef | Karim
2.5 | Testing a Parnter Should be able to delete his profile | 2 | Moataz | Youssef | Karim
2.6 | Testing a Partner's Profile Should be visible to other users | 2 | Moataz | Youssef | Karim
2.7 | Testing a Partner Should be able to add Board Members to his profile | 2 | Moataz | Youssef | Karim
2.8 | Testing a Partner Should be able to add Partners to his profile | 3 | Moataz | Youssef | Karim
2.9 | Testing a Partneer Should be able to add events to his profile | 2 | Moataz | Youssef | Karim
3 | Testing a Partner Should be able to add project to his past projects | 3 | Moataz | Youssef | Karim
3.1 | Testing a Partner Should be able to remove Board Members from thier profile | 2 | Moataz | Karim | Youssef
3.2 | Testing a Partner Should be able to remove Partners from his profile | 2 | Moataz | Karim | Youssef
3.3 | Testing a Partner Should be able to remove events from his profile | 2 | Moataz | Karim | Youssef
3.4 | Testing a Partner Should be able to remove a project from his past projects | 3 | Moataz | Karim | Youssef
3.5 | Testing a User Should be able to create a profile as an Educational Organization | 2 | Basem | Mahmoud | Sohail
3.6 | Testing an Educational Organization Should be able to View their Profile | 2 | Basem | Mahmoud | Sohail
3.7 | Testing an Educational Organization Should be able to edit their Profile | 3 | Basem | Mahmoud | Sohail
3.8 | Testing an Educational Organization Should be able to delete his profile | 2 | Basem | Mahmoud | Sohail
3.9 | Testing an Educational Organization's Profile Should be visible to other users | 2 | Basem | Mahmoud | Sohail
4 | Testing an Educational Organization Should be able to add Courses to their Profile | 2 | Basem | Mahmoud | Sohail
4.1 | Testing an Educational Organization Should be able to add Trainers to their Profile | 2 | Basem | Mahmoud | Sohail
4.2 | Testing an Educational Organization Should be able to add Certificates to their Profile | 2 | Basem | Mahmoud | Sohail
4.3 | Testing an Educational Organization Should be able to add Training Programs to their Profile | 2 | Basem | Mahmoud | Sohail
4.4 | Testing an Educational Organization Should be able to remove Courses from their Profile | 2 | Basem | Mahmoud | Sohail
4.5 | Testing an Educational Organization Should be able to remove Trainers from their Profile | 2 | Basem | Mahmoud | Sohail
4.6 | Testing an Educational Organization Should be able to remove Certificates from their Profile | 2 | Mahmoud | Basem | Sohail
4.7 | Testing an Educational Organization Should be able to remove Training Programs from their Profile | 2 | Mahmoud | Basem | Sohail
4.8 | Testing a User Should be able to create a profile as a Consultancy Organization | 2 | Mahmoud | Sohail | Basem
4.9 | Testing a Consultanct Should be able to View their Profile | 2 | Mahmoud | Sohail | Basem
5 | Testing a Consultanct Should be able to edit their Profile | 3 | Mahmoud | Sohail | Basem
5.1 | Testing a Consultanct Should be able to delete his profile | 2 | Mahmoud | Sohail | Basem
5.2 | Testing a Consultanct's Profile Should be visible to other users | 2 | Mahmoud | Sohail | Basem
5.3 | Testing a Consultant Should be able to add Board Members to his Profile | 2 | Mahmoud | Sohail | Basem
5.4 | Testing a Consultant Should be able to add Partners to his profile | 3 | Mahmoud | Sohail | Basem
5.5 | Testing a Consultant Should be able to add reports to his profile | 2 | Mahmoud | Sohail | Basem
5.6 | Testing a Consultant Should be able to add events to his Profile | 2 | Mahmoud | Sohail | Basem
5.7 | Testing a Consultant Should be able to remove Board Members from his Profile | 2 | Sohail | Basem | Mahmoud
5.8 | Testing a Consultant Should be able to remove Partners from his profile | 3 | Sohail | Basem | Mahmoud
5.9 | Testing a Consultant Should be able to remove reports from his profile | 2 | Sohail | Basem | Mahmoud
6 | Testing a Consultant Should be able to remove events from his Profile | 2 | Sohail | Basem | Mahmoud
6.1 | Testing a Member Should be able to View Masterclasses | 2 | Sohail | Basem | Mahmoud
6.2 | Testing a Member Should be able to require assesment with an Expert | 5 | Sohail | Basem | Mahmoud
6.3 | Testing a Member should be notified if his request is accepted | 3 | Sohail | Basem | Mahmoud
6.4 | Testing an Expert Should be able to Respond to requests by members | 5 | Sohail | Basem | Mahmoud
6.5 | Testing a Member Should be able to apply for a masterclass | 3 | Sohail | Basem | Mahmoud
6.6 | Testing a Member Should be able to View Recommended Masterclasses | 5 | Sohail | Basem | Mahmoud
6.7 | Testing an Expert Should be able to Assess Members | 5 | Sohail | Basem | Mahmoud
6.8 | Testing a Partner Should be able to Submit an Application of a Task | 3 | Karim | Youssef | Moataz
6.9 | Testing a Partner Should be able to Edit His Submitted Application as long as it hasn't been reviewed | 3 | Karim | Youssef | Moataz
7 | Testing a Partner Should be able to Negotiate over his Application | 5 | Karim | Youssef | Moataz
7.1 | Testing an Admin Should be able to View Applications | 2 | Karim | Youssef | Moataz
7.2 | Testing an Admin Should be able to review an Application | 2 | Karim | Youssef | Moataz
7.3 | Testing an Admin Should be able to Respond to Consultant Applications | 3 | Karim | Youssef | Moataz
7.4 | Testing an Admin Should be able to negotiate over an Application | 5 | Karim | Youssef | Moataz
7.5 | Testing a Consultant Should be able to view Applications | 2 | Karim | Youssef | Moataz
7.6 | Testing a Consultant Should be able to apply for Applications | 3 | Karim | Youssef | Moataz
7.7 | Testing a Tasks Should be visible to Users | 2 | Hossam | Gaafar | Kashlan
7.8 | Testing a Member should be able to view his recommended tasks | 5 | Hossam | Gaafar | Kashlan
7.9 | Testing a Member Should be able to Apply for a Task | 3 | Hossam | Gaafar | Kashlan
8 | Testing a Member Should be able to delete his application for a Task | 3 | Hossam | Gaafar | Kashlan
8.1 | Testing a Partner Should be able to Post a Task if he chose to proceed without consultancy | 3 | Kashlan | Hossam | Gaafar
8.2 | Testing a Partner Should be able to respond to requests | 3 | Kashlan | Hossam | Gaafar
8.3 | Testing an Admin Should be able to review Tasks | 3 | Kashlan | Hossam | Gaafar
8.4 | Testing an Admin Should be able to add extra attributes to a Task | 3 | Kashlan | Hossam | Gaafar
8.5 | Testing an Admin Should be able to edit a Task | 3 | Gaafar | Kashlan | Hossam
8.6 | Testing an Admin Should be able to delete a Task | 2 | Gaafar | Kashlan | Hossam
8.7 | Testing a Consultant Should be able to Respond to Member Applications for a Task | 3 | Gaafar | Kashlan | Hossam
8.8 | Testing a Consultant should be able to post a Task | 2 | Gaafar | Kashlan | Hossam